# Project Plan

## Project Goal

Operationalize a research-to-GTM workflow for FluidLogic's transition from motorsports and tactical performance into elite athlete demand.

## Workstream Map

| Workstream | Purpose | Owner | Status |

| --- | --- | --- | --- |

| Intake & Routing | Classify work and map the sequence of agency steps. | @team-lead + central-orchestrator | Planned |

| Research | Map competition, athlete pain, wedge options, and evidence gaps. | research-coordinator | Planned |

| Positioning | Translate race-proven credibility into premium athlete positioning. | distribution-coordinator + marketing-strategy | Planned |

| Pilot Design | Build the first 90-day commercial test. | learning-coordinator + experimentation | Planned |

| Sales Enablement | Turn positioning into proof, objection handling, and outreach materials. | distribution-coordinator | Planned |

| Launch Ops | Activate launch cadence and engagement operations. | distribution-coordinator + community-manager | Planned |

| Learning Loop | Track pilot response and refine GTM strategy. | learning-coordinator + analytics | Planned |

| Evidence Review | Validate claims before client-facing use. | truth-agent / risk-and-proof | Planned |

## Safe Parallel Work

- research the elite athlete landscape

- classify wedge opportunities by buyer, proof burden, and transferability

- draft positioning pillars tied to evidence

- define pilot success metrics and criteria

- prepare sales conversations and outreach assets

- capture launch feedback into a learning loop

## Gated Work

- public health or performance claims without evidence

- wellness positioning drift

- athlete-facing messaging without proof review

- launch activity before pilot proof and approval

- pricing or commercial commitments without stakeholder signoff

## Deliverables

workstreams/research.md

workstreams/positioning.md

workstreams/pilot-design.md

workstreams/launch-ops.md

workstreams/learning-loop.md

deliverables/fluidlogic-market-entry-wedge-options.md

deliverables/fluidlogic-pilot-brief.md

deliverables/fluidlogic-launch-playbook.md

evidence/evidence-ledger.md

## Next User Decision

Confirm whether the next milestone should be a full research packet, a positioning draft, or a pilot-ready commercial plan.