# FluidLogic AgencyOS Integration: Execution Status

## Team Lead Classification

Scope: Market transition project with multiple connected workstreams.

Risk level: High.

Known agencies: Research, Strategy & Positioning, Offer & Pilot Design, Sales Enablement, Content Studio, Launch, Risk & Proof, Insights.

Known constraints: preserve motorsports credibility, avoid generic wellness positioning, keep the workflow small-team compatible, maintain source-bounded claims.

Human decision owner: Juan Benitez / FluidLogic commercial leadership.

Needed output: research packet, premium positioning, pilot plan, launch plan, and learning loop.

## Status Summary

| Deliverable area | Status | Notes |

| --- | --- | --- |

| Project packet scaffold | Complete | The project structure and core governance files exist. |

| Intake and project brief | Complete | The scope, objective, guardrails, and outcome are defined. |

| Workstream map and agency routing | Complete | The process, agents, and handoff sequence are mapped. |

| Evidence ledger baseline | Complete | Source references and claim boundaries are documented. |

| Research report | Complete | A source-backed competitive and category analysis has been produced. |

| Risk & Proof review | Complete | Claim boundaries and risk language have been documented. |

| Positioning framework | Complete (draft) | The premium performance-system lane is defined and source-bound. |

| Pilot brief | Complete (draft) | A high-heat endurance/test segment concept is drafted with measurable KPI logic. |

| Launch playbook | In progress | The launch frame is defined, but a human approval step remains for target wedge selection. |

| Learning loop | In progress | The process is defined; customer feedback has not yet been captured in a live pilot. |

## Why the project is no longer blocked

The Research Agency and Risk & Proof Agency have now produced a working evidence-backed foundation for the next stage.

The key blocker is no longer a missing framework; it is a pending human decision on the exact wedge and commercial scope before full launch activation.

## Current Execution Condition

The project is now in a draft-ready operating state: the research and proof review support positioning, piloting, and launch design, but final commercial execution still requires human approval of the final wedge and target audience.

## Recommended Next Step

Have Juan or the designated commercial owner approve the recommended wedge (high-heat endurance / high-load performance athletes with coach involvement), then convert the draft positioning and pilot concept into final launch assets and a live learning loop.